## README
S5-02 — AI RISK REGISTER ENTRY
Evidence Item S5-02 ¦ Urielle AI Audit Template ¦ ISO 42001 cl.6.1 ¦ NIST AI RMF MAP 2.1
WHAT THIS WORKBOOK CONTAINS
Reusable Urielle AI template for Evidence Item S5-02 — AI Risk Register Entry.
Satisfies ISO 42001 cl.6.1 (AI risk assessment) and NIST AI RMF MAP 2.1.
SHEETS IN THIS WORKBOOK
1. README — Instructions, rating scales, and risk category guide.
2. Risk Register — Full risk register with identified risks, ratings, controls, residual risk. Pre-filled with NCAOS-Urielle.
3. Risk Heat Map — Visual likelihood × impact matrix showing inherent vs. residual risk positions.
4. Control Effectiveness — Assessment of control strength for each identified risk.
5. Template (Blank) — Clean blank register for new engagements.
RATING SCALES (USE CONSISTENTLY ACROSS ALL ENTRIES)
LIKELIHOOD: 1=Rare (<5% in 12mo) ¦ 2=Unlikely (5-20%) ¦ 3=Possible (20-50%) ¦ 4=Likely (50-80%) ¦ 5=Almost Certain (>80%)
IMPACT: 1=Negligible ¦ 2=Minor ¦ 3=Moderate ¦ 4=Major ¦ 5=Severe (catastrophic harm / regulatory action)
INHERENT RISK = Likelihood × Impact (before controls). RESIDUAL RISK = Re-rated after controls applied.
RISK RATING BANDS
CRITICAL (20-25): Immediate action required. No tolerance.
HIGH (12-19): Priority treatment. Senior owner. Tracked weekly.
MEDIUM (6-11): Active management. Monthly review.
LOW (1-5): Monitor. Annual review sufficient.
MANDATORY FIELDS PER RISK ENTRY (Evidence Request)
Risk ID — unique reference for tracking and cross-referencing
Risk Description — what could go wrong; cause; consequence
Likelihood rating (1–5) and Impact rating (1–5)
Inherent risk score (L×I before controls)
Controls — what is in place to reduce likelihood or impact
Residual risk score (L×I after controls)
Risk Owner — named individual (not a team)
RISK CATEGORIES (NCAOS-Urielle and general AI systems)
ENFORCEMENT INTEGRITY — incorrect enforcement decisions (allow/deny/alert)
AUDIT TRAIL — audit signal completeness and tamper resistance
SECURITY — unauthorised access, injection, tampering
BIAS / FAIRNESS — differential outcomes, policy authorship bias
GOVERNANCE — regulatory non-compliance, classification error
OPERATIONAL — performance, availability, dependency failures
PRIVACY — personal data processing without legal basis
BILATERAL / THIRD-PARTY — partner and supply chain risks
STRATEGIC — mission drift, reputational risk, model obsolesce

## Risk Register
S5-02 — AI RISK REGISTER ENTRY — NCAOS-Urielle EGS v1.0-rc
System: NCAOS-Urielle EGS v1.0-rc ¦ Risk Owner: William Hartono ¦ Date: June 2026 ¦ ISO 42001 cl.6.1 ¦ NIST AI RMF MAP 2.1
Inherent Risk = Likelihood × Impact BEFORE controls. Residual Risk = Re-rated AFTER controls. Rating: 1-5 scale (see README). Owner must be a named individual.
LIKELIHOOD: 1=Rare ¦ 2=Unlikely ¦ 3=Possible ¦ 4=Likely ¦ 5=Almost Certain IMPACT: 1=Negligible ¦ 2=Minor ¦ 3=Moderate ¦ 4=Major ¦ 5=Severe
Risk ID | Risk Category | Risk Description (What / Cause / Consequence) | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Controls in Place | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Rating | Risk Owner | Review Date / Status
R-EI-01 | ENFORCEMENT INTEGRITY | Policy enforcement engine produces incorrect allow/deny/alert decisions due to code regression, configuration error, or dependency update. Cause: code change introduces bug or breaking change. Consequence: AI system boundary policy violated; tenants may operate outside defined governance rules without detection. | 3 | 4 | 12 (12) | HIGH | 1. Daily regression suite (A-01): 229 known-payload test cases — any failure is blocking. 2. Rule-set hash integrity check (A-02): hourly SHA256 comparison vs. baseline. 3. Policy config gate (S3-05 RG-01): Auditor review before Admin approval of any policy change. 4. S4-04 Rollback Procedure tested (RT-2026-01) for rapid reversion. | 1 | 3 | 3 (3) | LOW | William Hartono | Jun 2026 — ACTIVE
R-EI-02 | ENFORCEMENT INTEGRITY | Rule-set drift or unauthorised modification: policy rule set diverges from version-controlled baseline due to tampering, infrastructure error, or accidental overwrite. Cause: unauthorised access or infrastructure failure. Consequence: enforcement decisions no longer match authorised policy; governance failure. | 2 | 5 | 10 (10) | MEDIUM | 1. SHA256 hash integrity monitoring (A-02): hourly check — mismatch triggers CRITICAL alert. 2. GitHub version control with commit-level history and access controls. 3. Admin Terminal RBAC: only Admin role can modify policy rule sets. 4. Bilateral review for significant rule set changes (S3-05 RG-01). | 1 | 4 | 4 (4) | LOW | William Hartono | Jun 2026 — ACTIVE
R-EI-03 | ENFORCEMENT INTEGRITY | Tenant isolation failure: enforcement decisions for one tenant contaminated by context from another tenant. Cause: software defect in tenant context isolation; shared state between tenant request handlers. Consequence: cross-tenant data leakage; governance boundary violation. | 2 | 5 | 10 (10) | MEDIUM | 1. Zod AuditSignal schema (B-01): tenant context validated at write time — mismatch triggers CRITICAL. 2. C-01 real-time cross-tenant context monitoring. 3. Phase 06 penetration testing included tenant isolation scenarios. 4. 6 synthetic tenant pair tests in pilot — 0 mismatches. | 1 | 5 | 5 (5) | LOW | William Hartono | Jun 2026 — ACTIVE
R-AT-01 | AUDIT TRAIL | AuditSignal completeness failure: boundary events occur but no AuditSignal record is written to EventStore. Cause: EventStore write failure, schema validation error, or software defect in audit-signal pipeline. Consequence: governance decisions cannot be audited retrospectively; ISO 42001 cl.9.1 and EU AI Act Art.12 obligations not met. | 2 | 5 | 10 (10) | MEDIUM | 1. B-01 real-time completeness monitoring: every boundary event checked for corresponding AuditSignal. 2. 3-layer Zod schema validation on every AuditSignal write. 3. EventStore write probe (B-02): synthetic write test every 5 min. 4. Pilot period: 4,847/4,847 events audited (100%). | 1 | 4 | 4 (4) | LOW | William Hartono | Jun 2026 — ACTIVE
R-AT-02 | AUDIT TRAIL | EventStore tampering or deletion: audit records modified or deleted after the fact. Cause: unauthorised access to EventStore; software defect allowing non-append operations. Consequence: audit trail integrity lost; impossible to verify governance decisions. | 2 | 5 | 10 (10) | MEDIUM | 1. EventStore designed as append-only (no delete or update operations exposed). 2. B-02 probe monitors record count for monotonic increase — decrease triggers CRITICAL. 3. Admin Terminal RBAC: Viewer and Operator roles cannot write to EventStore. 4. SHA256 hash monitoring provides integrity baseline. | 1 | 4 | 4 (4) | LOW | William Hartono | Jun 2026 — ACTIVE
R-SEC-01 | SECURITY | RBAC privilege escalation: a lower-privilege role (Viewer, Operator) gains access to higher-privilege API routes or data. Cause: API-layer role check missing or misconfigured. Consequence: unauthorised access to audit data or policy configuration; governance control undermined. Note: This risk was realised as INC-2026-01 (May 2026) — RBAC Viewer escalation on EventStore query route. REMEDIATED. | 3 | 4 | 12 (12) | HIGH | 1. INC-2026-01 REMEDIATED: API-level role check added to EventStore query route (May 2026). 2. Daily D-02 RBAC probe: all 4 roles tested against out-of-scope actions — must return 403. 3. Phase 06 STRIDE/AI-ML threat model included RBAC as a threat vector. 4. S2-03 FND-P05-01 CLOSED — corrective action validated. Residual risk remains LOW given daily automated monitoring. | 1 | 3 | 3 (3) | LOW | William Hartono | Jun 2026 — CLOSED (remediated)
R-SEC-02 | SECURITY | Dependency vulnerability: third-party package CVE introduces exploitable vulnerability in NCAOS-Urielle runtime. Cause: upstream package maintainer publishes security fix for a critical or high CVE. Consequence: exploitation could compromise enforcement engine, audit trail, or admin terminal. | 3 | 3 | 9 (9) | MEDIUM | 1. Weekly npm audit dependency scan (D-03): scans for CVEs. 2. Defined SLA: Critical CVE patched within 7 days; High within 30 days; Medium within 90 days. 3. Three Medium CVEs identified and resolved in 90-day pilot period (ZOD-2026-0039, ZOD-2026-0047, REACT-2026-0091). 4. Production build excludes dev dependencies. | 2 | 2 | 4 (4) | LOW | William Hartono | Dec 2026 — MONITORED
R-SEC-03 | SECURITY | Unauthorised API access: external actor probes or accesses @ncaos/api routes without valid credentials. Cause: credential compromise; brute force; API key leakage. Consequence: policy rule manipulation; audit log tampering; tenant data access. | 2 | 4 | 8 (8) | MEDIUM | 1. D-01 unauthorised access monitoring: 401/403 rate threshold (>5% = MEDIUM alert). 2. Phase 06 STRIDE/AI-ML threat model included authentication as attack vector. 3. Rate limiting middleware added (Phase 06 FND-P06-02 remediation). 4. API routes require valid credentials — no unauthenticated access. | 1 | 3 | 3 (3) | LOW | William Hartono | Dec 2026 — MONITORED
R-BF-01 | BIAS / FAIRNESS | Policy authorship bias: rule sets authored by a small bilateral team encode implicit governance norm assumptions that create differential enforcement across different tenant types or jurisdictions. Cause: limited diversity in policy rule authors. Consequence: governance enforcement that unintentionally disadvantages certain tenant types. | 3 | 3 | 9 (9) | MEDIUM | 1. Bilateral review with Toru (NCAOS Japan) at Phase 07 — independent policy review. 2. Bias disclosed in S2-01 (LIM-02), S2-02 (BIA-01), S2-04 (BF-01). 3. v1.1 roadmap: expanded stakeholder policy review with ≥3 external tenant organisations. 4. Policy consistency metric: 100% consistent decisions across tenant pairs in pilot testing. | 3 | 2 | 6 (6) | MEDIUM | William Hartono | v1.1 release — OPEN
R-BF-02 | BIAS / FAIRNESS | Temporal coverage gap: policy rules reflect governance norms as of June 2026; regulatory landscape (EU AI Act implementing acts) is still evolving and rules may become stale. Cause: regulatory guidance issued after rule-set authoring. Consequence: rules no longer reflect current regulatory requirements. | 3 | 2 | 6 (6) | MEDIUM | 1. 6-month review cycle (December 2026) includes regulatory landscape review. 2. Regulatory monitoring responsibility assigned to William Hartono. 3. S4-01 incident procedure includes regulatory reclassification as a trigger. | 2 | 2 | 4 (4) | LOW | William Hartono | Dec 2026 — MONITORED
R-GOV-01 | GOVERNANCE | Risk misclassification: NCAOS-Urielle is classified as Limited Risk but a scope change (e.g. addition of ML component, processing of personal data, Annex III use case) causes the system to be High-Risk without re-classification. Cause: material scope change not subjected to risk re-assessment. Consequence: High-Risk system operated without required Art.49 registration, Art.14 oversight design, etc. | 2 | 5 | 10 (10) | MEDIUM | 1. S2-05 Section 6 material change triggers list — any scope change triggers re-assessment. 2. S1-03 risk classification reviewed at 6-month cycle. 3. S4-03 Change Register: material changes flagged for S2-05 re-assessment. 4. Policy S5-01 Section 3.2: new use cases require policy amendment and governance review. | 1 | 4 | 4 (4) | LOW | William Hartono | Dec 2026 — ACTIVE
R-GOV-02 | GOVERNANCE | Regulatory non-compliance: EU AI Act implementing acts, delegated acts, or national guidance imposes new obligations not currently reflected in the governance framework. Cause: regulatory landscape continues to evolve post-June 2026. Consequence: non-compliance with applicable AI regulation. | 3 | 3 | 9 (9) | MEDIUM | 1. Regulatory monitoring by William Hartono (FHCA credential — ongoing regulatory CPD). 2. 6-month review cycle includes regulatory alignment check (S5-01 §6). 3. Urielle AI membership of AI Verify Foundation — early access to regulatory guidance. 4. ISO 42001 compliance framework designed to be regulatory-adaptive. | 2 | 2 | 4 (4) | LOW | William Hartono | Dec 2026 — MONITORED
R-OPS-01 | OPERATIONAL | Enforcement engine unavailability: @ncaos/shell process unavailable causing enforcement decisions to fail or default. Cause: infrastructure failure, out-of-memory, process crash. Consequence: AI boundary governance suspended; tenants may operate without enforcement during outage. | 2 | 4 | 8 (8) | MEDIUM | 1. A-03 heartbeat monitoring (60-second interval): heartbeat miss ×3 = HIGH alert. 2. S4-04 Rollback Procedure: recovery to prior version within 35 minutes (tested). 3. Safe-halt design: enforcement failure mode defaults to deny (fail-safe) at v1.0-rc design intent. 4. 99.97% uptime achieved in 30-day pilot period. | 1 | 3 | 3 (3) | LOW | William Hartono | Dec 2026 — MONITORED
R-OPS-02 | OPERATIONAL | Performance degradation under production load: API latency and throughput not formally benchmarked — actual production performance under concurrent tenant load is unknown. Cause: test environment does not represent production scale. Consequence: unacceptable response times in production; SLA breach. | 3 | 3 | 9 (9) | MEDIUM | 1. S2-05 COND-01/02: production performance benchmarking and load testing required before go-live. 2. Pilot data: P95 latency 189ms (single-node test env); peak 47 req/s. 3. S3-01 E-01/E-02 monitoring items defined — thresholds TBD post-benchmark. 4. Rollback procedure tested for rapid reversion if performance unacceptable post-go-live. | 2 | 3 | 6 (6) | MEDIUM | William Hartono | Pre-production — COND-01/02
R-PRI-01 | PRIVACY | Inadvertent personal data processing: a future version or configuration change causes the system to capture personal data (e.g. API payload content) that is not authorised by the current data governance framework. Cause: configuration change; new tenant type; expanded logging. Consequence: PDPA / GDPR breach; regulatory notification obligation triggered. | 2 | 4 | 8 (8) | MEDIUM | 1. S1-04 explicitly excludes personal data processing — scope constraint documented. 2. S2-05 material change trigger: any change that introduces personal data processing requires full re-evaluation. 3. S5-01 Policy P-05: explicit prohibition on personal data without legal basis. 4. S2-02 Data Lineage: no personal data in current system — formally declared. | 1 | 4 | 4 (4) | LOW | William Hartono | Dec 2026 — ACTIVE
R-BIL-01 | BILATERAL / THIRD-PARTY | Bilateral partner risk: Toru (NCAOS Japan) operates the Boundary Governance Layer and owns ADR-006 AuditSignal semantics. If the bilateral relationship is disrupted, governance of this shared architecture may be unclear. Cause: business relationship change; bilateral NDA dispute; partner unavailability. Consequence: architectural governance gap; uncertainty over IP ownership of shared components. | 2 | 3 | 6 (6) | MEDIUM | 1. Bilateral NDA: IP separation, derivative works ownership, and right of first negotiation documented. 2. ADR-006 design decisions documented in GitHub repository — independent of partner. 3. NCAOS-Urielle @ncaos/* packages under Urielle AI control in GitHub. 4. Role separation: Toru is research validation partner, not operational dependency for enforcement. | 1 | 2 | 2 (2) | LOW | William Hartono | Dec 2026 — MONITORED
R-STR-01 | STRATEGIC | Reputational risk: a security incident, governance failure, or bias finding in NCAOS-Urielle becomes publicly known and damages Urielle AI's reputation as an AI safety and governance practice. Cause: incident disclosure; regulatory finding; media coverage. Consequence: damage to Urielle AI brand; loss of client confidence; impact on FHCA credential standing. | 2 | 4 | 8 (8) | MEDIUM | 1. Comprehensive evidence suite (S1-01 to S5-02) demonstrates governance maturity. 2. Transparent incident disclosure policy (S4-01 §5 — external obligations). 3. ISO 42001 compliance framework and FHCA credential provide independent assurance baseline. 4. Bilateral review with NCAOS Japan provides independent governance validation. | 1 | 3 | 3 (3) | LOW | William Hartono | Dec 2026 — MONITORED
REGISTER SUMMARY: 17 risks identified ¦ Inherent: CRITICAL 0 ¦ HIGH 2 ¦ MEDIUM 15 ¦ LOW 0 ¦ Residual: HIGH 0 ¦ MEDIUM 2 ¦ LOW 15 ¦ Risk Owner: William Hartono (all risks)
TEMPLATE ROWS — Replace for new engagement. Add one row per identified risk.
[R-XX-01] | [CATEGORY] | [Risk Description: What could go wrong. Cause: what triggers it. Consequence: what harm results. Cross-reference relevant monitoring item from S3-01 if applicable.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Controls in place: 1. [control name] — description. 2. [control name] — description. Cross-reference S3-01 monitoring items and S2-03 evaluation findings where controls are tested.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED / COND-xx]
[R-XX-02] | [CATEGORY] | [Risk Description: What could go wrong. Cause: what triggers it. Consequence: what harm results. Cross-reference relevant monitoring item from S3-01 if applicable.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Controls in place: 1. [control name] — description. 2. [control name] — description. Cross-reference S3-01 monitoring items and S2-03 evaluation findings where controls are tested.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED / COND-xx]
[R-XX-03] | [CATEGORY] | [Risk Description: What could go wrong. Cause: what triggers it. Consequence: what harm results. Cross-reference relevant monitoring item from S3-01 if applicable.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Controls in place: 1. [control name] — description. 2. [control name] — description. Cross-reference S3-01 monitoring items and S2-03 evaluation findings where controls are tested.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED / COND-xx]
[R-XX-04] | [CATEGORY] | [Risk Description: What could go wrong. Cause: what triggers it. Consequence: what harm results. Cross-reference relevant monitoring item from S3-01 if applicable.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Controls in place: 1. [control name] — description. 2. [control name] — description. Cross-reference S3-01 monitoring items and S2-03 evaluation findings where controls are tested.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED / COND-xx]
[R-XX-05] | [CATEGORY] | [Risk Description: What could go wrong. Cause: what triggers it. Consequence: what harm results. Cross-reference relevant monitoring item from S3-01 if applicable.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Controls in place: 1. [control name] — description. 2. [control name] — description. Cross-reference S3-01 monitoring items and S2-03 evaluation findings where controls are tested.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED / COND-xx]
ATTESTATION — Risk Owner
I certify that this risk register represents a complete risk assessment for the AI system identified above, conducted in good faith. Risk ratings reflect genuine assessment against the defined scales. Controls listed are implemented (or planned with documented owners and dates). Residual risk ratings reflect honest assessment after controls — not aspirational future states.
Signed: _________________________ Name: William Hartono Title: Founder, Urielle AI / FHCA Date: ___________________________

## Risk Heat Map
RISK HEAT MAP — Inherent vs. Residual Risk Positions
L = Likelihood (1-5) ¦ I = Impact (1-5) ¦ Score = L×I ¦ Green shaded cell = risk position after controls (residual). Circle in cell = inherent risk position.
Impact \ Likelihood → | 1 | 2 | 3 | 4 | 5
Impact = 5 | ◆ R-EI-03 | ● R-EI-02 R-EI-03 R-AT-01 R-AT-02 R-GOV-01 | 15 | 20 | 25
Impact = 4 | ◆ R-EI-02 R-AT-01 R-AT-02 R-GOV-01 R-PRI-01 | ● R-SEC-03 R-OPS-01 R-PRI-01 R-STR-01 | ● R-EI-01 R-SEC-01 | 16 | 20
Impact = 3 | ◆ R-EI-01 R-SEC-01 R-SEC-03 R-OPS-01 R-STR-01 | ● R-BIL-01 ◆ R-OPS-02 | ● R-SEC-02 R-BF-01 R-GOV-02 R-OPS-02 | 12 | 15
Impact = 2 | ◆ R-BIL-01 | ◆ R-SEC-02 R-BF-02 R-GOV-02 | ● R-BF-02 ◆ R-BF-01 | 8 | 10
Impact = 1 | 1 | 2 | 3 | 4 | 5
LEGEND
● = Inherent risk position (before controls)
◆ = Residual risk position (after controls)
RISK ID REFERENCE
R-EI-01: Policy enforcement engine produces incorrect allow/deny/alert decisions due to c...
R-EI-02: Rule-set drift or unauthorised modification: policy rule set diverges from versi...
R-EI-03: Tenant isolation failure: enforcement decisions for one tenant contaminated by c...
R-AT-01: AuditSignal completeness failure: boundary events occur but no AuditSignal recor...
R-AT-02: EventStore tampering or deletion: audit records modified or deleted after the fa...
R-SEC-01: RBAC privilege escalation: a lower-privilege role (Viewer, Operator) gains acces...
R-SEC-02: Dependency vulnerability: third-party package CVE introduces exploitable vulnera...
R-SEC-03: Unauthorised API access: external actor probes or accesses @ncaos/api routes wit...
R-BF-01: Policy authorship bias: rule sets authored by a small bilateral team encode impl...
R-BF-02: Temporal coverage gap: policy rules reflect governance norms as of June 2026; re...
R-GOV-01: Risk misclassification: NCAOS-Urielle is classified as Limited Risk but a scope ...
R-GOV-02: Regulatory non-compliance: EU AI Act implementing acts, delegated acts, or natio...
R-OPS-01: Enforcement engine unavailability: @ncaos/shell process unavailable causing enfo...
R-OPS-02: Performance degradation under production load: API latency and throughput not fo...
R-PRI-01: Inadvertent personal data processing: a future version or configuration change c...
R-BIL-01: Bilateral partner risk: Toru (NCAOS Japan) operates the Boundary Governance Laye...
R-STR-01: Reputational risk: a security incident, governance failure, or bias finding in N...

## Control Effectiveness
CONTROL EFFECTIVENESS ASSESSMENT — NCAOS-Urielle EGS v1.0-rc
Control effectiveness rated: STRONG (fully implemented, tested, effective) ¦ MODERATE (implemented, partially tested) ¦ WEAK (designed but not tested / not fully implemented) ¦ PLANNED (not yet implemented)
Risk Ref | Control | Control Description | Evidence Reference | Effectiveness Rating | Test Date | [ Your Engagement ]
R-EI-01/02 | Regression Suite (A-01) | 229 known-payload test cases run daily. Any failure is blocking — system cannot be updated until suite passes. | S2-03 GATE-01 PASS; S3-04 daily runs | STRONG | Daily (automated) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-EI-01/02 | Hash Integrity (A-02) | SHA256 hash of active rule set compared against GitHub v1.0-rc baseline every hour and on startup. | S3-01 A-02; S3-04 alert log | STRONG | Hourly (automated) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-EI-03 | AuditSignal Zod Validation (B-01) | 3-layer Zod schema validation on every AuditSignal write. Real-time — any failure triggers CRITICAL alert. | S2-03 GATE-05 PASS; 4847/4847 audit records | STRONG | Real-time (automated) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-AT-01 | EventStore Write Probe (B-02) | Synthetic write probe every 5 minutes. Confirms EventStore write path is functional. | S3-01 B-02; S3-04 log | MODERATE | 5-min (automated) — latency spikes under peak load noted | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-AT-02 | Append-Only EventStore Design | EventStore exposes no delete or update operations. Record count monitored for monotonic increase. | S2-01 §4; S3-01 B-02 | STRONG | Design-time (no delete API exists) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-SEC-01 | RBAC Daily Probe (D-02) | All 4 role probes (Admin/Auditor/Operator/Viewer) run daily — confirm expected 403 for out-of-scope actions. | S2-03 GATE-06 PASS; INC-2026-01 CLOSED | STRONG | Daily (automated) — detected real RBAC finding | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-SEC-02 | Dependency Scan (D-03) | Weekly npm audit scan. CVE SLA: Critical 7d, High 30d, Medium 90d. | S3-04 ALT-011/017/018; npm audit logs | STRONG | Weekly (automated) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-SEC-03 | Rate Limiting Middleware | Rate limit middleware added to @ncaos/api (Phase 06 FND-P06-02). Prevents request flooding. | S2-03 FND-P06-02 CLOSED; Phase 06 pen tests | STRONG | Phase 06 pen test (11 scenarios) | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-BF-01 | Policy Consistency Metric | 100% decision consistency across tenant pairs tested in pilot. Bilateral review at Phase 07. | S2-04 §6 governance-equivalent test | MODERATE | June 2026 — broader stakeholder review deferred to v1.1 | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-GOV-01 | Material Change Trigger List | S2-05 §6 defines material changes that trigger re-assessment. S4-03 change register flags S2-05 needs. | S2-05 §6; S4-03 Change Register | STRONG | Designed — tested via INC-2026-01 corrective action process | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-OPS-01 | Enforcement Heartbeat (A-03) | 60-second heartbeat — missed × 3 = HIGH alert. 99.97% uptime in pilot. | S3-01 A-03; S3-02 monitoring report | MODERATE | Pilot period — production monitoring tooling TBD | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-OPS-02 | Performance Benchmarking | Indicative data collected (P95 189ms, 47 req/s peak). Formal benchmarking per S2-05 COND-01/02. | S3-02 Jun 2026; S2-05 COND-01/02 | PLANNED | Not yet formally tested — required before production go-live | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-PRI-01 | Personal Data Prohibition | S1-04 excludes personal data; S5-01 P-05 prohibits it without legal basis. Material change trigger covers scope expansion. | S1-04 §5; S5-01 §3.3; S2-02 §2 | STRONG | Design-time; reviewed at each governance cycle | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-BIL-01 | Bilateral NDA | IP separation, derivative works, right of first negotiation documented. ADR-006 independently documented. | Bilateral NDA; ADR-006; GitHub repository | STRONG | June 2026 — NDA signed; ADR-006 documented | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]
R-STR-01 | Evidence Suite and ISO 42001 Alignment | Comprehensive evidence suite (S1-01 to S5-02) and FHCA credential provide independent governance assurance. | S1-01 to S5-02; FHCA credential | MODERATE | Ongoing — evidence suite maintained at 6-month cycle | [STRONG / MODERATE / WEAK / PLANNED + evidence of testing]

## Template (Blank)
S5-02 — AI RISK REGISTER ENTRY — [ YOUR ENGAGEMENT ]
System: [System name] ¦ Risk Owner: [Name] ¦ Date: [DD Month YYYY] ¦ ISO 42001 cl.6.1 ¦ NIST AI RMF MAP 2.1
Inherent Risk = Likelihood × Impact BEFORE controls. Residual Risk = Re-rated AFTER controls. Owner must be a named individual.
LIKELIHOOD: 1=Rare ¦ 2=Unlikely ¦ 3=Possible ¦ 4=Likely ¦ 5=Almost Certain IMPACT: 1=Negligible ¦ 2=Minor ¦ 3=Moderate ¦ 4=Major ¦ 5=Severe
Risk ID | Risk Category | Risk Description (What / Cause / Consequence) | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Controls in Place | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Rating | Risk Owner | Review Date / Status
[R-XX-01] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-02] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-03] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-04] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-05] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-06] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-07] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-08] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-09] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-10] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-11] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
[R-XX-12] | [CATEGORY: ENFORCEMENT INTEGRITY / AUDIT TRAIL / SECURITY / BIAS / GOVERNANCE / OPERATIONAL / PRIVACY / BILATERAL / STRATEGIC] | [Risk Description: What could go wrong? Cause: what triggers this risk? Consequence: what harm results? Be specific — 'something bad happens' is not a risk description.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [1. Control name — what it does and how it reduces likelihood or impact. 2. Control name — description. Cross-reference monitoring items from S3-01 and evaluation findings from S2-03 where controls are tested and evidenced.] | [1-5] | [1-5] | [L×I] | [CRITICAL/HIGH/MEDIUM/LOW] | [Named individual] | [DD Mon YYYY / OPEN / MONITORED]
I certify that this risk register represents a complete and honest risk assessment for the AI system identified above. Risk ratings reflect genuine assessment. Residual risk ratings reflect the actual state after implemented controls — not aspirational future states after planned controls.
Signed: _________________________ Name: [Full Name] Title: [Title, Organisation] Date: [DD Month YYYY]